## Aim 1 - Public Health
Strategic Aim 1: Promote public health priorities
Number | Objective (What do you want to achieve?) | Outcome for patients | Progress to date - summarise current position and any key milestones for next steps | RAG Rating - how do you rate progress to date?
| Smoking | Ensure smoking status recorded regularly. Push help me quit | Increase use of Help me Quit.
| Obesity | Emphasise the fact that obesity is linked with a high number of health problems including diabetes and cancer. | Primary aim is to improve the rates of patients being weighed.
| Flu | Shared initiatives around IT and triggers. Improve collaboration with Community Pharmacists | Deborah Kalaji flu lead and disseminsating IT suggestions for practices. D/W Community pharmacists at cluster meet and individually. Searches and triggers for practices to flag the <65 groups not responded to invited and vaccines previously.

## Public Health
Priority | Situation | Objective | Outcome for patients | Output (practices) | Success criteria (cluster) | Outcome Indicator (PHOF) | Progress narrative | Progress (RAG) per quarter
Tobacco | 2016/17: Population Anglesey of adult smokers:57,728. Smokers 10,512 (18.2%) Estimated number to treat to reach 5% target: 526 and quarterly target of 131 | To contribute to the reduction in smoking prevalence in Anglesey by giving advice and making appropriate referrals to smoking cessation services. | People have access to information and advice about services and opportunities that enable them to maximise their health & Wellbeing | Up to date and accurate smoking status recorded of registered patients to help identify patients | System updated by each practice to identify smokers | Number of adults who smoke (& Tier 1 targets)
| Tier 1 targets :Q2 Activity (2017/18) :Number of treated adult smoker (target 5%) : Anglesey 4.1% and % of treated smokers quit at 4 weeks (CO validated) is 28.7% (target 40%). (comparable data against localities, BCUHB & Wales) |  | Through smoking prevention measures and smoking cessation, people have minimal risk of developing smoking related diseases. | Promote HMQ by disseminating self help information and referral to smoking cessation services (SSW & Pharmacy, HMQforBaby) | Self help resources on system by each practice and screens if available
Number of referrals to smoking cessation services of registered patients/ Cluster level & number of clients heard about HMQ by GP practice (Quarterly analysis but ,monthly available)
Promote awareness and MECC training to staff
Healthy Weight | Over 60% of adults in Anglesey are overweight or obese. 29% of adults in Anglesey undertake no regular physical activity. 21.2% of adults eat 5 more portions of fruit and vegatbles a day (23.8% Wales) | To contribute to increasing the level of healthy weight in children and adults on Anglesey by providing support, signposting to services and actively supporting public health campaigns | People have access to information and advice about services and opportunities that enable them to maximise their health & Wellbeing | Refer patients via social prescribing | Number of referrals to social prescribing in relation to weight management | % of working age adults of healthy weight
| (27.1%) in Wales in reception year are classified as overweight or obese (2016-17). BCU HB, at 29.5% (n=2,205), which is an increase from 28.6% in 2015-16. |  | People are healthy, active and do things to keep themselves healthy | Use of weight management services Inc. NERS | Number of referrals to specialist weight management services | children age 5 of healthy weight
| Children age 5 yrs. 32.5% overweight or obese in Anglesey (2017/18) |  | People are well supported in managing and protecting their physical, mental and social wellbeing | Accurately weigh patients and record | Increase in the Number of patients weighed (children and adults) Prioritise pre school children. | adults meeting physical activity guidelines
| Within Anglesey, Caergybi (Isle of Anglesey 003) is the MSOA with the highest number (n=108) of children aged 4-5 years who are obese, from a visual comparison made to deprivation (Figures 2 & 4) this is also one of the most deprived areas of North Wales. Seiriol (Isle of Anglesey 005) is the MSOA with the highest percentage (14.1%) of children aged 4-5 years who are obese, although this is one of the least deprived areas. |  | Inequalities that may prevent people from leading a healthy life are reduced through programmes tailored and designed to meet needs. | Raise the issue of weight through use of resources such as 10 Steps to healthy weight ( which includes promotion of breastfeeding)and 5 ways to wellbeing; on system, screens and promotion of campaigns | Self help resources on system by each practice and screens if available. | adults eating five fruit or veg portions a day
| The overweight or obese data also identifies Caergybi (Isle of Anglesey 003) as the MSOA with the highest number (n=241) of children aged 4-5 years who are overweight or obese. The MSOAs with the highest percentages (over 30%) of children aged 4-5 years who are overweight or obese are Talybolion (Isle of Anglesey 004), Seiriol (Isle of Anglesey 005) an area of lowest deprivation, Canolbarth Mon (Isle of Anglesey 006) and Caergybi (Isle of Anglesey 003), an area of high deprivation. |  |  |  | Promote awareness and MECC training to staff
Immunisation: Childhood | Cover report Nov 2018) 96.6% (6 in 1) Age 1 years old, Up to date in schedule by age 5yrs. 84.4%, MMR by age 5yrs. 93.3% (target 95%) Oct17to Sept 18 Anglesey: 5 in1 97.2%; Up to date 2yrs 96.8%, 4yrs 89.3%, 5yrs 93.4%; MMR 2dose 94.1% | To ensure children are protected against preventable diesease | People have access to information and advice about services and opportunities that enable them to maximise their health & Wellbeing | Identify patients that are outstanding and follow up and record on child health system | Increase number of those who receive 3 doses of hexavalent by age 1 and 2 doses of MMR by age 5. | % of children who receive 3 doses of hexavalent (6in1) by age 1. % of children receiving 2 doses of MMR by age 5 (target 95%) (cover data)
Anglesey cluster Flu: | 2017/2018 data: 65 yrs.+ 71.6% (target 75%) 2-3 yr. olds= 55.9% & 65yrs and under at risk 53.7% (55% target) | To ensure eligible children, adults and protected groups are protected against flu. | Interventions to improve people's health are based on good quality and timely research and best practice | Identify a lead to run the Vaccination Campaign in each practice, and Identify a lead to identify eligible patient | Practices with named leads who follow recommendations | Flu vaccine take up (IVOR)
| Jan 8 2019 : 2/3 year olds: 56.3%; 65+ 69.8%, at risk and under 65 years 48.2% |  |  | identify eligible patient and ensure timely ordering of vaccines in line with WHC | Number of practices ordering required vaccines by August
|  |  |  | Encourage staff to receive flu jab | Number of staff receiving flu jab
|  |  |  | Shared initiatives around IT and triggers. Improve collaboration with Community Pharmacists | Number of eligible patients receiving flu vaccinations
|  |  |  | Promote positive flu campaign messages | Number of practices actively promoting the annual campaign
|  |  |  | Regularly review uptake and variation of vacs and imms | Review of uptake and variation at a regular basis
Identify a Cluster rep to attend the BCU Flu Planning Group

## Aim 2 -sustainability & access
Strategic Aim 2: To ensure the sustainability of core GP services and access arrangements that meet the reasonable needs of local patients including any agreed collaborative arrangements
Number | Objective (What do you want to achieve?) | Outcome for patients | Progress to date - summarise current position and any key milestones for next steps | RAG Rating - how do you rate progress to date?
| Recruitment & Retention | Still difficulty in recruiting locums and limited number of applicants for long term posts | BCUHB recruitment initiatives. Need to ensure workpressure and demands not excessive, some risk from GPs in particular leaving busy/stressful posts.
| Pharmacist clinical practitioner | Improved quality chronic disease managements whilst freeing up GP appoinments | Taking time to change role of pharamcists to be face to face clinicians and to expand areas of clinical confidence e.g. currently focused HT. Plan to develop osteoporosis management, diabetes management and respiratory disease managemnet. Training/mentoring for pharmacists needs supporting.
| Advanced Phyio practitioner | Initial plan had been the hope that quick access to brief initial advice would lead to less ongoing pain and morbiditiy from acute musculoskeletal problems. Also the hope is to reduce demand on secondary care and reduce burden on GP appointments from musculoskeletal conditions. | Appears to have an impact on secondary care referrals. Still uncear if early intervention reduces overall demand compared to delayed physio. Still unclear if reducing demand on primary care. Difficult to assess impact on GP work pressure.
| Winter Planning | COPD rescue packs. Flu immunisation. Consider expanding MEC to reduce demand on OOH and primary care (pilot proposal at this stage) | Flu immunisation slightly hampered by delays in the new adjuvant vaccine delivery but Anglesey comparing well to other areas on immunisation rates so far. COPD rescue packs - unclear how well we rolled this out last year, for pushing again this year, consider asking the health board pharmacy team to assist.
| Reduce Demand from high demand patients | Consider focusing attention on patients attending most frequently at GP and at Secondary care in order to focus future work on these patients | Only a recent plan and needs expansion. Useful to consider spending some cluster time on these patients to identify frequent themes.
To add a new row - click onto this cell and then the right hand mouse button and choose "insert" "entire row"

## Aim 3 - Care closer to home
Strategic Aim 3: Provide Care Closer to home
Number | Objective (What do you want to achieve?) | Outcome for patients | Progress to date - summarise current position and any key milestones for next steps | RAG Rating - how do you rate progress to date?
| Hospital at home/MEC | Expanding care at home can lead to improved outcomes and reduced pressures on hospitals | Good feedback from patients and GPs. Feasibility and acceptability good. No clear evidence that our current approach is reducing hospital admissions. Need to consider slight change of approach. We're currently considering targetting our most vulnerable patients and working with the newly developed CRTs to creast holistic plans with a particular focus on the steps needed for an individual patient when they have
| Community Resource Teams | Integrated care with more rapid assessment and delivery of joined up health and social services care. | Nearing a point of starting CRT service, ongoing discussion with health and community teams. Still some planning needed around site of bases, particularly with integrating district nursing teams.
| Care Planning inc TEP | Previous TEP (Treatment escalation plan) work showed a possible reduction in hospital admission for our most frail Nursing home patients and increased likelihood of dying at home. | Some recent issues around the appropriateness of TEP use and the adequacy in trainng to use the forms/plans appropriately. New versions of TEP produced and trainng plans in place. Still some difficulty in encouraging use without funding GPs to carry out the work. In discussion with LMC and health board. Current plan is to encourage use in care homes and to look at incorporating the TEP in to a "shared" care plan for use by the CRT team.
To add a new row - click onto this cell and then the right hand mouse button and choose "insert" "entire row"

## Aim 4 - Focused specialty
Strategic Aim 4: Focused specialty
Number | Objective (What do you want to achieve?) | Outcome for patients | Progress to date - summarise current position and any key milestones for next steps | RAG Rating - how do you rate progress to date?
| Information Technology | GP practcies are all having to change computer systems in the next year. This will place pressure on practices but the eventual hope is that we will see improved collaborative working and improved use of IT functionality and potential. | All Anglesey practices have chosed to migrate to Microtest. We expect the initial migrations to begin taking place from April 2019. There is still a degree of uncertainty regarding the amount of support we will get and still no clear certainty of how well the new system will work. (The system is still being completed)
To add a new row - click onto this cell and then the right hand mouse button and choose "insert" "entire row"

## Aim 5 - Social Prescribing
Strategic Aim 5 - Social prescribing
Number | Objective (What do you want to achieve?) | Outcome for patients | Progress to date - summarise current position and any key milestones for next steps | RAG Rating - how do you rate progress to date?
| Community Linc Scheme | Focus on improved community cohesiveness and on "wellbeing" with a particular focus on the 5 ways to wellbeing. Ther service has been in place but not well utilised by GPs as yet. W e now have link workers (Local are co-ordinators) allocated to each practie and are improving the links with practices. | We still have some difficulties with a safe and robust referral system. Our hope had been that we would be able to use the Elemental system, partiuclalry as this also incorporates effective follow up of clients referred and collects baseline and follow up data for us. We are waiting for the tendering process for this acrross the BCUHB to take place. In the meantime we are hoping to place the LACs at least some of the working weeks withing GP practices -t his can be limited by available practice space. We're also looking at focusing on patients placing the most demand on primary and secondary services, the idea being that we might release most pressure on services by targetting hte "wellbeing" of these patients/clients.
To add a new row - click onto this cell and then the right hand mouse button and choose "insert" "entire row"

## Aim 6 - Other
Strategic Aim 6 - Other Locality Issues
Number | Objective (What do you want to achieve?) | Outcome for patients | Progress to date - summarise current position and any key milestones for next steps | RAG Rating - how do you rate progress to date?
To add a new row - click onto this cell and then the right hand mouse button and choose "insert" "entire row"
Note on C5: ch108133: